## Sheet1
|  | February |  |  |  | March |  |  |  |  | April |  |  |  | May |  |  | Summary
| Week: | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | Hours | Percentage
Tasks:
Studying and Specifying Requirements |  | February 1: 12; February 2: 12; February 3: 8; February 4: 6 | 38 | 19%
Design |  | February 3: 4; February 4: 6; March 1: 12; March 2: 4; March 3: 3 | 29 | 14.5%
Implementation |  | March 1: 4; March 2: 12; March 3: 12; March 4: 12; March 5: 8; April 1: 5; April 2: 5; April 3: 5 | 63 | 31.5%
Testing |  | March 4: 2; March 5: 4; April 1: 8; April 2: 2; April 3: 2 | 18 | 9%
Writing Docs |  | April 2: 4; April 3: 4 | 8 | 4%
Final Report |  | April 1: 2; April 2: 2; April 3: 2; April 4: 12; May 1: 12; May 2: 2 | 32 | 16%
Presentation |  | May 1: 4; May 2: 4; May 3: 4 | 12 | 6%
Total Hours |  | 12 | 12 | 12 | 12 | 16 | 16 | 15 | 14 | 12 | 15 | 13 | 13 | 12 | 16 | 6 | 4 | 200